## Defects
Defect ID | Submitted By | Submitted Date | Defect Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Project Team | 2026-09-16 | DEF-001 ¦ Patient Flow ¦ Monthly admission count was not updating correctly after applying date filter. | Sprint 2 | nafisa | Logical | Corrected date filtering logic. | 2026-09-16 | Closed | Severity: High ¦ Priority: High
2 | Project Team | 2026-09-16 | DEF-002 ¦ Patient Flow ¦ Dashboard showed incorrect total admissions for the filtered department. | Sprint 2 | sowmitha | Logical | Fixed department filter calculation. | 2026-09-16 | Closed | Severity: Medium ¦ Priority: High
3 | Project Team | 2026-09-16 | DEF-003 ¦ Resource Utilization ¦ Bed occupancy percentage was calculated incorrectly. | Sprint 3 | sirivalli | Logical | Corrected occupancy formula. | 2026-09-16 | Closed | Severity: High ¦ Priority: High
4 | Project Team | 2026-09-16 | DEF-004 ¦ Resource Utilization ¦ Available bed count did not match total beds minus occupied beds. | Sprint 3 | Deepika | Logical | Updated KPI calculation. | 2026-09-16 | Closed | Severity: Medium ¦ Priority: High
5 | Project Team | 2026-09-16 | DEF-005 ¦ Geographic Analysis ¦ Some patient locations were missing from the map. | Sprint 4 | tanvi | Logical | Cleaned and standardized location values | 2026-09-16 | Closed | Severity: Medium ¦ Priority: Medium
6 | Project Team | 2026-09-16 | DEF-006 ¦ Dashboard ¦ Charts were not refreshing correctly after changing filters. | Sprint 4 | sarthak | Logical | Fixed filter/data refresh logic. | 2026-09-16 | Closed | Severity: High ¦ Priority: High
7 | Project Team | 2026-09-16 | DEF-007 ¦ Dashboard ¦ Dashboard displayed empty charts when no records matched filters. | Sprint 4 | keerthi | Logical | Added empty-data handling. | 2026-09-16 | Closed | Severity: Low ¦ Priority: Medium
8 | Project Team | 2026-09-16 | DEF-008 ¦ Dashboard ¦ KPI values differed between Python calculation and dashboard. | Sprint 4 | divya | Logical | Validated and corrected KPI logic. | 2026-09-16 | Closed | Severity: High ¦ Priority: High
9 | Project Team | 2026-09-16 | DEF-009 ¦ UI ¦ Long chart labels were overlapping on smaller screens. | Sprint 4 | rushi | User Interface | Adjusted chart layout and labels. | 2026-09-16 | Closed | Severity: Low ¦ Priority: Low
10 | Project Team | 2026-09-16 | DEF-010 ¦ Deployment ¦ Application failed to load correctly after deployment. | Sprint 4 | abhi | User Interface | Fixed deployment configuration and dependencies. | 2026-09-16 | Closed | Severity: High ¦ Priority: High

## Sheet2
Logical
User Interface
Maintainability
Standards
Others