## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 |  | US-01 | Collect healthcare operational datasets | Must | None | Sowmitha,Sarthak,Indhu | Completed
Sprint 1 |  | US-02 | Clean and preprocess admissions and patient data | Must | US-01 | Tanvi,Nafisa | Completed
Sprint 1 |  | US-03 | Handle missing values, duplicates and data types | Must | US-02 | Nafisa,Abhi | Completed
Sprint 1 |  | US-04 | Select relevant attributes for operational analysis | Must | US-01 | Deepika,Rushi | Completed
Sprint 1 |  | US-05 | Create integrated cleaned dataset | Must | US-02, US-04 | Divya,Sarthak | Completed
Sprint 1 |  | US-06 | Define and validate healthcare KPIs | Must | US-05 | Deepika,Divya,Indhu | Completed
Sprint 2 |  | US-07 | Analyze patient admissions and discharge trends | Must | US-05 | Rushi,Sirivalli | Completed
Sprint 2 |  | US-08 | Analyze treatment demand and departmental workload | Must | US-05 | Abhi,Rushi | Completed
Sprint 2 |  | US-09 | Build patient flow visualizations | Must | US-06, US-07 | Deepika,Nafisa | Completed
Sprint 2 |  | US-10 | Identify operational bottlenecks and high-demand areas | Should | US-07, US-08 | Sarthak,Sowmitha | Completed
Sprint 3 |  | US-11 | Calculate bed utilization and capacity metrics | Must | US-05, US-06 | Tanvi,Deepika,Sirivalli | Completed
Sprint 3 |  | US-12 | Analyze workforce and staffing efficiency | Must | US-05, US-06 | Sowmitha,Sarthak | Completed
Sprint 3 |  | US-13 | Create resource performance scorecards | Must | US-11, US-12 | Indhu,Abhi | Completed
Sprint 3 |  | US-14 | Compare utilization with defined operational benchmarks | Should | US-11, US-13 | Nafisa,Deepika,Sarthak | Completed
Sprint 4 |  | US-15 | Build patient distribution geographic analysis | Must | US-05 | Tanvi,Keerthi | Completed
Sprint 4 |  | US-16 | Build healthcare service coverage analysis | Should | US-15 | Sirivalli,Keerthi | Completed
Sprint 4 |  | US-17 | Integrate patient flow and resource intelligence | Must | US-09, US-13 | All Team Members | Completed
Sprint 4 |  | US-18 | Build executive dashboard with key operational KPIs | Must | US-17 | Rushi,Divya,Tanvi,Sarthak | Completed
Sprint 4 |  | US-19 | Add interactive filters and dashboard navigation | Must | US-18 | All Team Members | Completed
Sprint 4 |  | US-20 | Deploy and test complete dashboard | Must | US-18, US-19 | Rushi,Sarthak | Completed
Sprint 4 |  | US-21 | Validate KPIs, filters, calculations and data consistency | Must | US-20 | Sarthak,Nafisa,Abhi | Completed
Sprint 4 |  | US-22 | Document project and prepare final presentation | Should | US-20, US-21 | Nafisa,Deepika,Divya | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 50 | 10 | 8 | 9 | 9 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Identify and collect relevant healthcare datasets | 2026-07-22 | 2026-07-24 | Sarthak | Data Collection | completed | 6 | Day 1: 6
US-01 | T-02 | Review dataset structure, columns and data quality | 2026-07-22 | 2026-07-24 | Abhi | Data Analysis | completed | 4 | Day 1: 4
US-02 | T-03 | Load raw datasets using Pandas | 2026-07-23 | 2026-07-24 | Deepika | Data Processing | completed | 3 | Day 2: 3
US-02 | T-04 | Handle missing values and duplicates | 2026-07-23 | 2026-07-24 | Divya | Data Cleaning | completed | 5 | Day 2: 5
US-03 | T-05 | Standardize dates, categorical values and data types | 2026-07-23 | 2026-07-24 | Indhu | Data Cleaning | completed | 5 | Day 3: 5
US-04 | T-06 | Select relevant columns for project KPIs | 2026-07-23 | 2026-07-24 | Tanvi | Data Analysis | completed | 4 | Day 3: 4
US-05 | T-07 | Merge related datasets where required | 2026-07-23 | 2026-07-24 | Sirivalli | Data Integration | completed | 6 | Day 4: 6
US-05 | T-08 | Export cleaned/processed dataset | 2026-07-23 | 2026-07-24 | Keerthi | Data Processing | completed | 3 | Day 4: 3
US-06 | T-09 | Define Total Patients, Admissions, Discharges and LOS KPIs | 2026-07-23 | 2026-07-24 | Sowmitha | KPI Definition | completed | 5 | Day 5: 5
US-06 | T-10 | Validate KPI calculations against source data | 2026-07-23 | 2026-07-24 | Rushi | Validation | completed | 4 | Day 5: 4
US-05 | T-11 | Create project repository and folder structure | 2026-07-23 | 2026-07-24 | Nafisa | GitHub | completed | 2 | Day 6: 2
US-05 | T-12 | Update README with data pipeline and setup instructions | 2026-07-23 | 2026-07-24 | Indhu | Documentation | completed | 3 | Day 6: 3
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | No major impediment | Dataset sources and task ownership confirmed.
Sprint 1 | Day 2 | Some columns have inconsistent formats | Team standardized column names and data types.
Sprint 1 | Day 3 | Missing values identified | Cleaning rules defined and applied in Pandas.
Sprint 1 | Day 4 | Duplicate records found | Duplicates reviewed and removed where justified.
Sprint 1 | Day 5 | Related datasets use different keys | Team mapped common identifiers before merging.
Sprint 1 | Day 6 | KPI definitions needed clarification | Team documented KPI formulas and assumptions.
Sprint 1 | Day 7 | Validation differences found | Checked filters, aggregation and source records.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-22 | 2026-07-24 | Sowmitha | Start documenting assumptions earlier | Stop changing columns without informing the team | Continue sharing dataset findings | Documented the data collection and cleaning decisions.
2 | Sprint 1 | 2026-07-22 | 2026-07-24 | Sarthak | Start testing cleaning code with sample rows | Stop relying on manual Excel edits | Continue using reproducible Pandas scripts | Added validation checks after cleaning.
3 | Sprint 1 | 2026-07-22 | 2026-07-24 | Deepika | Start communicating dependency issues sooner | Stop working on disconnected copies of data | Continue reviewing merged datasets | Agreed on one processed dataset.
4 | Sprint 1 | 2026-07-22 | 2026-07-24 | Tanvi | Start recording KPI formulas | Stop assuming KPI definitions are obvious | Continue validating calculations | Added KPI definitions to project documentation.
5 | Sprint 1 | 2026-07-22 | 2026-07-24 | Rushi | Start making smaller commits | Stop pushing unrelated changes together | Continue reviewing pull requests | Standardized GitHub workflow.
6 | Sprint 1 | 2026-07-22 | 2026-07-24 | Nafisa | Start testing setup on a clean environment | Stop leaving deployment/testing until the end | Continue helping with integration | Created a basic setup checklist.
7 | Sprint 1 | 2026-07-22 | 2026-07-24 | Divya | Start raising blockers during stand-up | Stop duplicating tasks | Continue supporting teammates | Reassigned tasks to remove overlap.